## Dashboard
ESG Action Plan Dashboard
Auto-summary of action status, priorities, due dates, and resource needs from the Action Plan sheet. Sample data is included for illustration and should be replaced before use.
Total Actions | Completed | In Progress / At Risk | Overdue | Due in 30 Days | Total Budget (RM)
8 | 0 | 3 | 0 | 1 | 14500
Status | Count | % of Total |  | Priority | Count |  | Pillar | Open | Completed | Total
Not Started | 4 | 50% |  | Priority 1: Immediate / Critical | 1 |  | Environmental | 3 | 0 | 3
In Progress | 2 | 25% |  | Priority 2: Short-Term Risk Control | 3 |  | Social | 2 | 0 | 2
At Risk | 1 | 12.5% |  | Priority 3: Medium-Term System Improvement | 4 |  | Governance | 3 | 0 | 3
Delayed | 1 | 12.5% |  | Priority 4: Long-Term Strategic Development | 0 |  | Cross-cutting | 0 | 0 | 0
Completed | 0 | 0% |  | Priority 5: Monitor | 0
On Hold | 0 | 0%
Cancelled | 0 | 0%
Resource Type | Budget Estimate (RM) | Actions |  | Focus Area | Count | Review Question | Suggested Management Action
Internal effort | 0 | 3 |  | Overdue actions | 0 | Which actions are overdue and why? | Escalate blockers; revise resources or deadlines.
Budget | 0 | 0 |  | Priority 1 open | 1 | Are critical actions progressing? | Review weekly until closed.
Training | 11500 | 3 |  | Pending approvals | 2 | Which budgets/resources need approval? | Route to approver with decision deadline.
System / digital tool | 0 | 1 |  | Evidence missing after completion | 0 | Are completed actions evidence-backed? | Obtain and file proof before closure.
External advisor | 0 | 0
Supplier engagement | 3000 | 1
Capital expenditure | 0 | 0
Legal / technical review | 0 | 0
Certification / assurance | 0 | 0
None | 0 | 0

## Action Plan
ESG Action Plan Template
Purpose: convert ESG gaps into practical actions with owners, deadlines, resources, evidence, status, and management review fields. Replace sample rows before use.
Gap ID | Source of Gap | ESG Pillar | ESG Topic | Requirement / Expectation | Gap Description | Gap Type | Root Cause | Affected Boundary | Severity | Urgency | Priority | Risk / Opportunity Link | ESG Objective | Action Required | Milestone / Interim Deliverable | Responsible Owner | Accountable Approver | Supporting Department(s) | Start Date | Due Date | Target Quarter | Resource Type | Resource Details | Budget Estimate (RM) | External Support Needed? | KPI / Target | Evidence Required | Dependencies / Constraints | Status | % Complete | Closure Evidence Link / Location | Effectiveness Review Result | Reporting Note / Disclosure Relevance | Last Updated | Days to Due | Due Status | Closure Readiness | Management Approval Needed? | Approval Status | Comments
SAMPLE-01 | ESG Checklist | Governance | Transparency and Risk Management | Assign data owners for material ESG topics | No formal data ownership matrix for ESG indicators. | Governance | ESG data collected by departments but not formally assigned or reviewed. | Company-wide | High | Short-term (0-6 months) | Priority 2: Short-Term Risk Control | Weak data controls may affect customer submissions and reporting credibility. | Strengthen ESG data accountability | Create ESG data ownership matrix and assign owners by topic and metric. | Draft matrix reviewed by department heads | ESG Lead | Senior Management | HR; EHS; Procurement; Finance; Production | 2026-06-15 | 2026-07-15 | 2026-Q3 | Internal effort | ESG lead time; department review workshop | 0 | No | 100% material ESG metrics assigned owner and reviewer | Approved data ownership matrix; meeting minutes | Requires department head confirmation | In Progress | 40% |  |  | Report as data quality improvement action | 2026-06-01 | 41 | On track | Not ready | No | Not Required | Sample row - replace before use
SAMPLE-02 | Gap Analysis | Environmental | Emissions | Calculate Scope 1 and Scope 2 GHG emissions | Emissions calculation workbook not yet prepared. | Data | Electricity and fuel data exist but are not consolidated into GHG calculation. | Main manufacturing site | High | Medium-term (6-18 months) | Priority 3: Medium-Term System Improvement | Customer climate questionnaires may request emissions data. | Improve emissions reporting readiness | Prepare Scope 1 and Scope 2 calculation workbook using monthly electricity and fuel records. | Electricity and fuel records collected for baseline year | EHS / OHS | ESG Committee | Finance; Maintenance / Facilities | 2026-07-01 | 2026-09-30 | 2026-Q3 | Training | Basic GHG accounting training; emission factor review | 6000 | Conditional | 2026 baseline emissions calculated and reviewed | Utility bills; fuel invoices; GHG calculation workbook; emission factor sources | Needs monthly data from Finance and Maintenance | Not Started | 0% |  |  | Disclose baseline once reviewed | 2026-06-01 | 118 | On track | Not ready | Yes | Pending | Sample row - replace before use
SAMPLE-03 | Customer request | Governance | Supply Chain Traceability and Due Diligence | Strengthen supplier origin and traceability evidence | Priority natural rubber suppliers have incomplete origin documentation. | Supplier | Supplier onboarding form does not request origin and traceability evidence consistently. | Natural rubber suppliers | Critical | Short-term (0-6 months) | Priority 2: Short-Term Risk Control | Traceability gaps may affect buyer due diligence and market access. | Improve supplier traceability | Issue updated supplier ESG questionnaire and collect origin, licence, and batch evidence from priority suppliers. | Questionnaire issued to top 10 suppliers | Procurement / Supply Chain | Senior Management | ESG Lead; Compliance / Legal | 2026-06-15 | 2026-12-31 | 2026-Q4 | Supplier engagement | Supplier briefing; follow-up calls; document review | 3000 | No | 80% of priority suppliers screened by end-2026 | Supplier questionnaires; declarations; purchase records; traceability register | Supplier response depends on document availability | At Risk | 25% |  |  | Include as supplier due diligence progress update | 2026-06-01 | 210 | On track | Not ready | Yes | Pending | Sample row - replace before use
SAMPLE-04 | Internal audit | Social | Occupational Health and Safety | Review HIRARC for high-risk production areas | HIRARC not updated after new equipment installation. | Procedure | Change management process did not trigger OHS review. | Production line 2 | High | Short-term (0-6 months) | Priority 2: Short-Term Risk Control | Unreviewed hazards may lead to workplace incidents or audit findings. | Strengthen OHS controls | Update HIRARC, communicate revised controls, and verify PPE requirements. | Site walk-through completed | EHS / OHS | Senior Management | Production; Maintenance / Facilities; HR | 2026-06-10 | 2026-08-31 | 2026-Q3 | Internal effort | Safety officer time; toolbox briefing | 0 | No | HIRARC updated for 100% high-risk areas in scope | Updated HIRARC; toolbox attendance; inspection records | Requires production downtime for walk-through | In Progress | 55% |  |  | Disclose under OHS improvement actions if material | 2026-06-01 | 88 | On track | Not ready | No | Not Required | Sample row - replace before use
SAMPLE-05 | Worker grievance | Social | Human Rights and Social Impact | Communicate grievance channel and non-retaliation commitment | Some workers are unaware of the formal grievance channel. | Training | Induction materials do not explain grievance steps in worker languages. | All workers; migrant workers | Medium | Short-term (0-6 months) | Priority 3: Medium-Term System Improvement | Weak grievance awareness may prevent early issue identification. | Improve worker access to grievance mechanisms | Update induction materials and conduct bilingual briefing on grievance channel. | Briefing materials translated | HR | Senior Management | ESG Lead; Compliance / Legal | 2026-06-20 | 2026-07-31 | 2026-Q3 | Training | Translation; briefing sessions | 1500 | No | 100% workers briefed; grievance posters displayed | Training records; translated materials; communication photos | Need worker language confirmation | Not Started | 0% |  |  | May be reported as social compliance improvement | 2026-06-01 | 57 | On track | Not ready | No | Not Required | Sample row - replace before use
SAMPLE-06 | Legal compliance register | Environmental | Waste | Maintain complete scheduled waste evidence | Scheduled waste consignment notes are incomplete for one month. | Evidence | Waste vendor evidence not filed centrally. | Waste storage area | High | Immediate (0-3 months) | Priority 1: Immediate / Critical | Missing evidence may affect compliance readiness and audit outcomes. | Close scheduled waste evidence gap | Retrieve missing consignment notes and create monthly evidence filing checklist. | Vendor contacted for missing documents | EHS / OHS | Compliance / Legal | Procurement / Supply Chain; Finance | 2026-06-01 | 2026-06-30 | 2026-Q2 | Internal effort | EHS filing review; vendor follow-up | 0 | No | 100% scheduled waste records complete for 2026 | Consignment notes; waste inventory; vendor licence | Depends on vendor response | Delayed | 35% |  |  | Do not disclose detail unless material; track internally | 2026-06-01 | 26 | Due <30 days | Not ready | No | Not Required | Sample row - replace before use
SAMPLE-07 | Self-assessment | Environmental | Water | Track monthly water consumption by site | Water use is available through bills but not recorded in KPI tracker. | Data | No recurring monthly update process. | Main site | Medium | Medium-term (6-18 months) | Priority 3: Medium-Term System Improvement | Water data gaps reduce reporting quality and resource efficiency analysis. | Improve water data tracking | Create monthly water tracker and assign Finance/EHS review process. | Water tracker template created | EHS / OHS | ESG Lead | Finance; Production | 2026-08-01 | 2026-10-31 | 2026-Q4 | System / digital tool | Spreadsheet tracker; monthly review meeting | 0 | No | Monthly water data recorded within 10 working days of bill receipt | Water bills; water tracker; review notes | Requires bill access from Finance | Not Started | 0% |  |  | Report water data when full-year record is available | 2026-06-01 | 149 | On track | Not ready | No | Not Required | Sample row - replace before use
SAMPLE-08 | Management review | Governance | Anti-Corruption | Deliver ABAC and conflict-of-interest refresher training | Refresher training has not been delivered to procurement and sales teams. | Training | Annual training plan did not include ESG governance topics. | Procurement; Sales | Medium | Medium-term (6-18 months) | Priority 3: Medium-Term System Improvement | Weak awareness may increase integrity and customer confidence risks. | Strengthen business ethics controls | Conduct ABAC and conflict-of-interest training and collect declarations. | Training provider/materials confirmed | Compliance / Legal | Senior Management | HR; Procurement / Supply Chain; Sales / Customer Service | 2026-07-15 | 2026-09-15 | 2026-Q3 | Training | Trainer/materials; declaration forms | 4000 | No | 100% targeted employees trained and declarations completed | Training attendance; declarations; training materials | Need attendance scheduling | Not Started | 0% |  |  | Report under business ethics / anti-corruption training | 2026-06-01 | 103 | On track | Not ready | No | Not Required | Sample row - replace before use
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
[36 empty] | No due date | Not ready
Formulas:
Days to Due = IF(OR([Due Date]="",[Status]="Completed"),"",[Due Date]-TODAY())
Due Status = IF([Due Date]="","No due date",IF([Status]="Completed","Closed",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=30,"Due <30 days","On track"))))

## Gap Intake
Gap Intake Register
Use this sheet to capture gaps from the ESG Checklist, audits, customer requests, supplier due diligence, grievances, and management reviews before converting them into action plan rows.
Gap ID | Source | Checklist / Assessment Status | ESG Pillar | ESG Topic | Requirement / Expectation | Current Status | Gap Description | Gap Type | Root Cause | Affected Boundary | Severity | Urgency | Suggested Priority | Suggested Action | Proposed Owner | Resource Need | Due Date | Evidence Required | Action Plan Ref / Notes

## RACI & Owners
ESG RACI and Owner Directory
Clarify who is Responsible, Accountable, Consulted, and Informed for key action areas. Update owner names before use.
RACI Role | Meaning | [5 empty] | Owner Name | Function / Department | Role in Action Plan | Email / Contact | Escalation Point | Notes
Responsible | Person or function that performs the task.
Accountable | Person or function that owns the outcome and approves completion.
Consulted | Person or function that provides input or technical advice.
Informed | Person or function that must be updated on progress or decisions.
Action Area | Responsible | Accountable | Consulted | Informed | Review Frequency | Evidence / Output
ESG action plan maintenance | ESG Lead | Senior Management | Department owners | ESG Committee | Monthly / quarterly | Updated action plan and progress tracker
Environmental data and evidence | EHS / OHS | ESG Lead | Finance; Maintenance; Production | Senior Management | Monthly | Utility data, waste records, permits, monitoring reports
Labour and human rights actions | HR | Senior Management | Compliance / Legal; Worker representatives | ESG Committee | Quarterly | Training records, grievance log, worker records
Supplier due diligence actions | Procurement / Supply Chain | Senior Management | ESG Lead; Compliance / Legal | Relevant customers where needed | Quarterly | Supplier questionnaires, risk ratings, CAP tracker
GHG emissions calculation | EHS / OHS | ESG Committee | Finance; Maintenance; External advisor | Board / Owner | Annually with quarterly data updates | GHG calculation workbook and source data
Corrective action closure | Action owner | Accountable approver | ESG Lead; Internal Audit / QA | Senior Management | Monthly until closure | Closure evidence and effectiveness review
Budget approval | Finance | Senior Management / Board / Owner | Action owner; ESG Lead | ESG Committee | As needed | Budget approval record
External ESG disclosure | ESG Lead | Board / Owner / Senior Management | Data owners; Legal; Sales | Relevant departments | Before disclosure | Approved ESG report / customer response

## Budget & Resources
Budget and Resource Plan
Use this sheet to estimate funding, manpower, training, systems, supplier engagement, and external support needed to close ESG gaps.
Action ID | ESG Pillar | ESG Topic | Action Summary | Resource Type | Budget Estimate (RM) | Funding Source | Internal Man-Days | External Support / Vendor | Approval Required? | Approval Status | Budget Owner | Target Approval Date | Actual Spend (RM) | Notes
SAMPLE-01 | Governance | Transparency and Risk Management | Create ESG data ownership matrix and assign owners by topic and metric. | Internal effort | 0 |  |  |  | No | Not Required
SAMPLE-02 | Environmental | Emissions | Prepare Scope 1 and Scope 2 calculation workbook using monthly electricity and fuel records. | Training | 6000 |  |  |  | Yes | Pending
SAMPLE-03 | Governance | Supply Chain Traceability and Due Diligence | Issue updated supplier ESG questionnaire and collect origin, licence, and batch evidence from priority suppliers. | Supplier engagement | 3000 |  |  |  | Yes | Pending
SAMPLE-04 | Social | Occupational Health and Safety | Update HIRARC, communicate revised controls, and verify PPE requirements. | Internal effort | 0 |  |  |  | No | Not Required
SAMPLE-05 | Social | Human Rights and Social Impact | Update induction materials and conduct bilingual briefing on grievance channel. | Training | 1500 |  |  |  | No | Not Required
SAMPLE-06 | Environmental | Waste | Retrieve missing consignment notes and create monthly evidence filing checklist. | Internal effort | 0 |  |  |  | No | Not Required
SAMPLE-07 | Environmental | Water | Create monthly water tracker and assign Finance/EHS review process. | System / digital tool | 0 |  |  |  | No | Not Required
SAMPLE-08 | Governance | Anti-Corruption | Conduct ABAC and conflict-of-interest training and collect declarations. | Training | 4000 |  |  |  | No | Not Required

## Evidence Closure
Evidence-Based Closure Checklist
Use this sheet to confirm that completed actions are supported by evidence and that effectiveness has been reviewed.
Action ID | Action Summary | Evidence Required | Evidence File / Location | Evidence Status | Reviewed By | Review Date | Closure Status | Effectiveness Check | Risk Reduced? | Ready for Management Sign-Off? | Retention / Audit Notes | Comments
SAMPLE-01 | Create ESG data ownership matrix and assign owners by topic and metric. | Approved data ownership matrix; meeting minutes |  |  |  |  | Not ready
SAMPLE-02 | Prepare Scope 1 and Scope 2 calculation workbook using monthly electricity and fuel records. | Utility bills; fuel invoices; GHG calculation workbook; emission factor sources |  |  |  |  | Not ready
SAMPLE-03 | Issue updated supplier ESG questionnaire and collect origin, licence, and batch evidence from priority suppliers. | Supplier questionnaires; declarations; purchase records; traceability register |  |  |  |  | Not ready
SAMPLE-04 | Update HIRARC, communicate revised controls, and verify PPE requirements. | Updated HIRARC; toolbox attendance; inspection records |  |  |  |  | Not ready
SAMPLE-05 | Update induction materials and conduct bilingual briefing on grievance channel. | Training records; translated materials; communication photos |  |  |  |  | Not ready
SAMPLE-06 | Retrieve missing consignment notes and create monthly evidence filing checklist. | Consignment notes; waste inventory; vendor licence |  |  |  |  | Not ready
SAMPLE-07 | Create monthly water tracker and assign Finance/EHS review process. | Water bills; water tracker; review notes |  |  |  |  | Not ready
SAMPLE-08 | Conduct ABAC and conflict-of-interest training and collect declarations. | Training attendance; declarations; training materials |  |  |  |  | Not ready

## Guidance
How to Use the ESG Action Plan Template
This tool is designed for Malaysian rubber processors and manufacturers using the MRC ESG Guidelines and ESG Checklist.
Step | What to do | Output | Key Field | How to complete
1. Import gaps | Copy gaps from the ESG Checklist, self-assessment, audits, supplier due diligence, customer requests, incident/grievance logs, or management review into the Gap Intake Register. | Gap Intake Register | Gap ID | Use a unique reference, such as GAP-001 or SAMPLE-01. Keep this consistent across all sheets.
2. Classify each gap | Classify the ESG pillar, ESG topic, gap type, severity, urgency, root cause, affected boundary, and evidence required. | Prioritised gap list | Requirement / Expectation | State the checklist item, legal requirement, customer request, certification expectation, or internal policy requirement.
3. Convert into action | Move priority gaps into the Action Plan and write a practical action that states what will be done, by whom, by when, and with what resources. | Action Plan row | Gap Description | Describe the gap factually: what is missing, weak, incomplete, unsupported, or not implemented.
4. Assign accountability | Assign Responsible Owner, Accountable Approver, supporting departments, and management approval needs. Use the RACI sheet for clarity. | RACI / ownership record | Root Cause | Explain why the gap exists, such as no owner, no SOP, lack of training, missing data source, supplier non-response, or budget constraint.
5. Define resources | Identify internal effort, budget, training, systems, supplier engagement, external advisor support, capital expenditure, or certification/assurance needs. | Budget and Resource Plan | Severity | Rate the possible impact if the gap remains open: Low, Medium, High, or Critical.
6. Track progress | Update status, percent complete, milestones, delays, budget approvals, and due-status flags at least monthly or quarterly. | Progress tracker and Dashboard | Urgency | Select the implementation timing: Immediate, Short-term, Medium-term, Long-term, or Monitor.
7. Close with evidence | Do not close an action until the required evidence is filed, reviewed, and the effectiveness check confirms the risk or gap has been reduced. | Evidence Closure checklist | Priority | Use Priority 1 or 2 for high-risk gaps, urgent customer/regulatory matters, serious evidence gaps, safety/labour/compliance risks, or unresolved audit findings.
8. Review and report | Use the Dashboard and progress table for management review and, where appropriate, ESG reporting or customer responses. | Management review record / reporting note | Action Required | Write a concrete action using action verbs: develop, assign, collect, verify, train, update, implement, screen, calculate, review, or approve.
|  |  | Evidence Required | Identify the record that proves completion: policy, SOP, register, training record, supplier declaration, bill, calculation workbook, audit report, CAP closure, or management minutes.
|  |  | Closure Readiness | The formula returns Ready for closure only when Status is Completed and a closure evidence location is provided.
Reference Basis | How this template reflects the Guidelines
Checklist and supporting tools | The Guidelines position supporting tools as practical companions to translate ESG expectations into action, evidence, and measurable progress.
Gap analysis | The gap analysis outputs include a Gap Analysis Register and ESG Improvement Action Plan that records gaps, resource needs, actions, owners, due dates, and evidence.
Action plan | The action plan should clearly state what will be done, who is responsible, when it will be completed, resources needed, and evidence proving completion.
Management review | Management review should review key gaps, resources, timelines, assigned actions, due dates, evidence, and status.

## Lists
Dropdown Lists and Priority Rules
This sheet powers data validation in the template. Edit lists carefully if you need company-specific options.
Source of Gap | ESG Pillar | ESG Topic | Gap Type | Severity | Urgency | Priority | Owner Function | Status | Resource Type | Approval Status | Yes / No | Checklist Status | Evidence Status
ESG Checklist | Environmental | Deforestation | Policy | Low | Immediate (0-3 months) | Priority 1: Immediate / Critical | Senior Management | Not Started | Internal effort | Not Required | Yes | Implemented | Not collected
Self-assessment | Social | Sustainable Land Use and Natural Ecosystem Conservation | Procedure | Medium | Short-term (0-6 months) | Priority 2: Short-Term Risk Control | Board / Owner | In Progress | Budget | Pending | No | Partially Implemented | Collected
Gap Analysis | Governance | Biodiversity | Implementation | High | Medium-term (6-18 months) | Priority 3: Medium-Term System Improvement | ESG Lead | At Risk | Training | Approved | Conditional | Not Implemented | Reviewed
Internal audit | Cross-cutting | Emissions | Evidence | Critical | Long-term (18-36 months) | Priority 4: Long-Term Strategic Development | ESG Committee | Delayed | System / digital tool | Rejected | Not Applicable | Not Applicable | Approved
Customer request |  | Material Use and Circularity | Data |  | Monitor | Priority 5: Monitor | EHS / OHS | Completed | External advisor | Conditional |  | Information unavailable | Evidence missing
Supplier due diligence |  | Hazardous Substances | Supplier |  |  |  | HR | On Hold | Supplier engagement |  |  | Under review
Legal compliance register |  | Energy | Compliance |  |  |  | Procurement / Supply Chain | Cancelled | Capital expenditure
ESG Risk Register |  | Soil Health | Training |  |  |  | Production |  | Legal / technical review
Stakeholder feedback |  | Water | Governance |  |  |  | Maintenance / Facilities |  | Certification / assurance
Incident / grievance |  | Waste | Performance |  |  |  | Finance |  | None
Management review |  | Human Rights and Social Impact | Disclosure |  |  |  | Compliance / Legal
Reporting process |  | Diversity, Equity and Inclusion | Other |  |  |  | Quality Assurance / Internal Audit
Certification audit |  | Workers' Rights |  |  |  |  | Sales / Customer Service
|  | Occupational Health and Safety |  |  |  |  | IT / Systems
|  | Child Labour |  |  |  |  | External Advisor
Forced or Compulsory Labour
Rights of Indigenous Peoples
Local Communities
Freedom of Association and Collective Bargaining
Training and Development
Pay and Equal Remuneration
Supply Chain Traceability and Due Diligence
Corporate Governance
Business Ethics
Transparency and Risk Management
Tax Practices
Anti-Corruption
Stakeholder Engagement
Regulatory Risk and Public Policy
Severity / Urgency Pattern | Suggested Priority | Suggested Timeline
Critical + Immediate | Priority 1: Immediate / Critical | Complete immediately or within 0-3 months
Critical or High + Short-term | Priority 2: Short-Term Risk Control | Complete within 0-6 months
Medium + Medium-term | Priority 3: Medium-Term System Improvement | Complete within 6-18 months
Long-term strategic investment | Priority 4: Long-Term Strategic Development | Plan within 18-36 months
Low risk / monitor only | Priority 5: Monitor | Review annually or when context changes